## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As an unregistered user, I want to be able to register an account using the portal so that I can create an account with username and password so I can access my investor functionalities. | 3 | khaled | youssef abo bakr | youssef waly
1.1 | As a logged in user, I want to be able to log out from my account so that I can keep my information safe. | 2 | youssef abobakr | khaled | omar fatayry
1.2 | As an unregistered and registered user I want to view the electronic journal of approved companies by the reviewer so that I can view them. | 3 | youssef abobakr | khaled | omar fatayry
1.4 | As a logged in user, I want to be able to edit my profile , so that I can keep my details updated. //authentication | 3 | ahmed hesham | mohamed alaa | mohamed atef
2.1 | As a logged in investor, I want to be able to choose which type of company I want to establish so that I can fill the right application form. | 1 | omar fatayry | ahmed hesham | andrew
2.2 | As a logged in investor, I want to fill a company establishment form so that I can begin the process of establishing my own company. | 2 | mohamed alaa | mohamed atef | khaled
2.3 | As a logged in investor, I want to update the form after being disapproved and commented on by the establishment lawyer so that I can fix any mistakes stated by the lawyer and continue with the process of establishing the company. | 3 | ahmed reyad | bassem | mohamed alaa
2.4 | As a logged in investor, I want to track my requests/Case status so that I can estimate the time remaining and update my request if needed. | 3 | ahmed reyad | bassem | mohamed alaa
2.6 | As a logged in investor, I want to see all of my established companies and my unestablished companies that are waiting for approval so that I can review their details. | 3 | ahmed hesham | mohamed alaa | mohamed atef
2.7 | As a logged in investor, I want to view the estimated fees after filling the company establishment form so that I can pay them upon approval. | 1 | bassem | ahmed reyad | ahmed hesham
3 | As a staff*, I want to login with my email/username and password using the portal so that I could access the internal portal to perform any functionality according to my type. | 3 | youssef waly | andrew | bassem
3.2 | As a logged in staff*, I want to view case details so that I can get information about the cases. | 1 | mohamed alaa | mohamed atef | khaled
3.3 | As a logged in entity employee, I want to access my workpage, so that I could view all my due tasks. | 3 | omar fatayry | ahmed hesham | andrew
4 | As a logged in admin, I want to have access to the registration page so that I can register entity employees. | 3 | khaled | youssef abo bakr | youssef waly
5 | As a logged in establishment lawyer, I want to have access to the application form so that I can fill a form for an investor. | 2 | mohamed alaa | mohamed atef | khaled
5.1 | As a logged in establishment lawyer, I want to review applications filled by the investor and assigned to me so that I can approve or disapprove them. | 3 | mohamed atef | youssef waly | ahmed reyad
5.2 | As a logged in establishment lawyer, I want to be able to recalculate the fees so that I can view the updated fees after updating the form. | 1 | bassem | ahmed reyad | mohamed atef
5.3 | As a logged in establishment lawyer, I want to add comments to the disapproved applications by me so that I can notify the investor of the problem at hand. | 3 | andrew | omar fatayry | youssef abobakr
5.4 | As a logged in establishment lawyer, I want to update the forms that are assigned to me after being disapproved and commented on by the reviewer so that I can fix mentioned mistakes from the reviewer and the process of establishing the company can continue. | 3 | youssef waly | andrew | bassem
5.5 | As a logged in establishment lawyer, I want to resubmit disapproved forms from the reviewer that are assigned to me after updating them so that the process of establishing the company continues. | 3 | bassem | ahmed reyad | ahmed hesham
5.7 | As a logged in establishment lawyer, I want to view the estimated fees after filling the company establishment form so that I can inform the investor(my client). | 1 | bassem | ahmed reyad | ahmed hesham
6 | As a logged in reviewer, I want to review the applications assigned to me filled or reviewed by the establishment lawyer so that I can approve or disapprove them. | 3 | mohamed atef | youssef waly | ahmed reyad
6.1 | As a logged in reviewer, I want to add comments to the disapproved applications by me so that the assigned establishment lawyer can update them. | 3 | andrew | omar fatayry | youssef abobakr
2 | As an investor, I want to login with my email/username and password using the portal so that I can perform investor’s functionalities. | 2 | omar fatayry | ahmed hesham | andrew