## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a logged in user, I want to be able to log out from my account so that I can keep my information safe. | 2 | youssef abo bakr
1.1 | As a logged in investor, I want to update the form after being disapproved and commented on by the establishment lawyer so that I can fix any mistakes stated by the lawyer and continue with the process of establishing the company. | 3 | ahmed reayad
1.2 | As a logged in investor, I want to see all of my established companies and my unestablished companies that are waiting for approval so that I can review their details. | 3 | ahmed hesham
1.4 | As a logged in establishment lawyer, I want to have access to the application form so that I can fill a form for an investor. | 3 | mohamed alaa
1.5 | As a logged in establishment lawyer, I want to review applications filled by the investor and assigned to me so that I can approve or disapprove them. | 1 | mohamed atef
1.6 | As a logged in establishment lawyer, I want to update the forms that are assigned to me after being disapproved and commented on by the reviewer so that I can fix mentioned mistakes from the reviewer and the process of establishing the company can continue. | 3 | waly
1.7 | As a logged in establishment lawyer, I want to be able to recalculate the fees so that I can view the updated fees after updating the form. | 1 | bassem
1.8 | As a logged in establishment lawyer, I want to resubmit disapproved forms from the reviewer that are assigned to me after updating them so that the process of establishing the company continues. | 2 | bassem
1.9 | As a logged in establishment lawyer, I want to view the estimated fees after filling the company establishment form so that I can inform the investor(my client). | 1 | bassem
1.91 | As an investor, I want to login with my email/username and password using the portal so that I can perform investor’s functionalities. | 2 | omar fatayry
1.92 | As a logged in entity employee, I want to sort the task items assigned to me by case ID or case creation date so that I can easily filter my tasks. | 2 | andrew
1.93 | As a logged in investor, I want to be able to choose which type of company I want to establish so that I can fill the right application form. | 2 | omar fatayry
1.94 | As a logged in reviewer, I want to review the applications assigned to me filled or reviewed by the establishment lawyer so that I can approve or disapprove them. | 2 | mohamed atef
Backend:
2 | As a logged in investor, I want to pay my fees after being approved by the reviewer so that I could establish my company and the details of the company be published on the portal and the external entities get notified. | 7 | youssef waly
2.1 | As a logged in Investor, I want to view my notifications so that I can be aware of any changes in any of my cases’ status. | 7 | khaled
2.2 | As a logged in staff*, I want to search through all cases so that I can find specific ones. | 7 | mohamed alaa
2.3 | As a logged in admin, I want to be able to upload JSON files so that it can be converted to UI as forms. | 7 | ahmed reyad