## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | As a logged in investor, I want to fill a company establishment form so that I can begin the process of establishing my own company. | 3 | Khaled
1.1 | As a logged in investor, I want to see all of my established companies and my unestablished companies that are waiting for approval so that I can review their details. | 1 | Khaled | 1
1.2 | As a logged in investor, I want to update the form after being disapproved and commented on by the establishment lawyer so that I can fix any mistakes stated by the lawyer and continue with the process of establishing the company. | 3 | Alaa | 1 | As a logged in investor, I want to create a form of a company then update it when needed.
1.3 | As a logged in admin, I want to be able to delete companies(forms) if needed , so that I can fix any problem. | 1 | Alaa | 1 | As a logged in investor, I want to create a form of a company then it can be deleted when needed.
2 | As an unregistered user, I want to be able to register an account using the portal so that I can create an account with username and password so I can access my investor functionalities. | 3 | Youssef abobakr
2.1 | As a logged in investor, I want to be able to view my profile , so that I can view all my details. | 1 | Youssef abobakr | 2
2.2 | As a logged in investor, I want to be able to edit my profile , so that I can keep my details updated. | 3 | Bassem | 2 | As an investor, I want to be able to create an investor profile then view my profile.
2.3 | As a logged in investor/admin, I want to be able to delete my/a profile in special casses, so that I fix any prolem. | 1 | Bassem | 2 | As an investor, I want to be able to create an investor profile then delete my profile.
3 | As a logged in admin, I want to have access to the registration page so that I can create lawyer. | 3 | Omar elfatayry
3.1 | As a logged in lawyer, I want to be able to view my profile , so that I can view all my details. | 1 | Omar elfatayry | 3
3.2 | As a logged in admin, I want to be able to edit lawyers profile , so that I can keep thier details updated. | 3 | ahmed reyad | 3 | As a logged in admin, I want to be able to create a lawyer account then this profile can be viewed by the lawyer/admin.
3.3 | As a logged in admin, I want to be able to delete lawyers profile , so that I can revoke their authorization if needed. | 1 | ahmed reyad | 3 | As a logged in admin, I want to be able to create a lawyer account then this profile can be deleted.
4 | As a logged in admin, I want to have access to the registration page so that I can create reviewers. | 3 | youssef waly
4.1 | As a logged in reviewer, I want to be able to view my profile , so that I can view all my details. | 1 | Andrew | 4
4.2 | As a logged in admin, I want to be able to edit reviewers profile , so that I can keep thier details updated. | 3 | Andrew | 4 | As a logged in admin, I want to be able to create a reviewer account then this profile can be viewed by the reviewer/admin.
4.3 | As a logged in admin, I want to be able to delete reviewers profile , so that I can revoke their authorization if needed. | 1 | youssef waly | 4 | As a logged in admin, I want to be able to create a reviewer account then this profile can be deleted.
5 | As a logged in admin, I want to have access to the registration page so that I can create other admins. | 3 | mohmamed atef
5.1 | As a logged in admin, I want to be able to view my profile , so that I can view all my details. | 1 | ahmed hesham | 5
5.2 | As a logged in admin, I want to be able to edit my profile , so that I can keep my details updated. | 3 | ahmed hesham | 5 | As a logged in admin, I want to be able to create an admin profile then view this profile.
5.3 | As a logged in admin, I want to be able to delete admins profile , so that I can revoke their authorization if needed. | 1 | mohmamed atef | 5 | As a logged in admin, I want to be able to create an admin profile then delete this profile if needed.